## Slide 1
Improving Cost Estimation and Project Planning
A Data-Driven Approach for Contract-Based Furniture Projects
THAKUR VISHALKUMAR VINOD
IITM Online BS Degree Program
Indian Institute of Technology, Madras

## Slide 2
Slide 2: Executive Summary
Project Overview
Data-driven approach for The Furniture Master Interiors
Analysis of 25 completed projects (Jan-Jun 2025)
Focus on cost estimation accuracy and timeline management
Key Challenges
Systematic cost underestimation in quotations
Frequent project delays affecting profitability
Impact on customer satisfaction and business growth
Project Goals
Develop accurate cost estimation models
Improve project timeline management
Enhance profitability and customer satisfaction
Average Cost Overrun
6.76%
Total impact: ₹944,491 across all projects
Average Project Delay
3.8 days
Maximum delay: 7 days

## Slide 3
Slide 3: Problem Statement
Inaccurate Cost Estimations
6.76%
Average Cost Overrun
88%
Projects Over Budget
₹944,491 total profit erosion across analyzed projects
Quoting process lacks risk-adjusted pricing
Direct impact on profit margins (40-68% reduction in net
profitability)
Project Delays
3.8
Average Delay (Days)
7
Maximum Delay (Days)
Longer projects accumulate more delay days (R²=0.86)
Main causes: supplier delays, client changes, labor shortages
Direct impact on customer satisfaction and business reputation

## Slide 4
Slide 4: Methodology
Data Collection
6-month period (Jan-Jun 2025)
25 completed projects from The Furniture Master
Sources: quotations, purchase records, bills, site reports
Cross-verified with physical invoices and delivery slips
Analysis Approach
Data cleaning: standardizing units, correcting spellings
Descriptive statistics: mean, median, standard deviation
Correlation analysis: relationships between variables
Trend analysis: patterns in cost overruns and delays
Excel Analysis
PivotTables, charts, conditional formatting for
business insights
Python Modeling
Regression models, statistical tests, data visualization

## Slide 5
Slide 5: Key Findings - Cost Analysis
Quoted vs. Actual Cost
Key Insight
Only 3 projects (12%) stayed within budget, while 22 projects (88%) exceeded quoted costs
6.76%
Average Cost Overrun
₹944,491
Total Financial Impact
Figure no. 1
Cost Overrun Distribution
Business Impact
For every ₹100,000 quoted, the actual cost is ₹106,760, creating a systematic profit gap
Figure no. 1
Figure no. 2

## Slide 6
Slide 6: Key Findings - Project Size Impact
Project Size vs. Cost Overrun
Key Insight
Medium projects (151-300 sq.ft.) show the highest volatility in cost overruns, making them the most unpredictable category
Small Projects (≤150 sq.ft.)
5-6% average overrun
Most predictable
Medium Projects (150-300 sq.ft.)
7-8% average overrun
Highest volatility
Large Projects (>300 sq.ft.)
6-7% average overrun
Moderate predictability
Business Recommendation
Apply size-based buffers: Small (5-7%), Medium (8-10%), Large (6-8%) to account for varying risk profiles
Figure no. 3

## Slide 7
Slide 7: Key Findings - Delay Analysis
3.8
Average Delay (Days)
7
Maximum Delay (Days)
Project Duration vs. Delay
Key Insight
Strong correlation (R²=0.86) between project duration and absolute delay days
Main Causes of Delays
Supplier Delays
Late delivery of plywood, laminates, fevicol
Client Changes
Extra cabinets, design modifications
Labor Shortages
Especially during festival seasons
Design Revisions
Mid-project changes requiring rework
Business Recommendation
Apply proportional timeline buffers (5-10% of estimated duration)
Figure no. 4

## Slide 8
Slide 8: Root Cause Analysis
Frequency vs. Impact Analysis
Key Insight
High-frequency issues create the largest cumulative financial damage, even when individual impact is moderate
Top 3 Issues by Financial Impact
1
Client-Requested Changes
₹221,141 total impact | 6 projects | 6.2% avg overrun
2
Supplier Delays in Plywood
₹195,630 total impact | 5 projects | 7.34% avg overrun
3
Labor Shortages (Festival Season)
₹122,413 total impact | 3 projects | 7.2% avg overrun
Strategic Opportunity
Addressing the top 3 issues would mitigate ₹539,184 (57%) of the total overrun amount
Figure no. 5

## Slide 9
Slide 9: Recommendations
Data-Driven Quoting Buffer
Default: 7%
Size-based adjustments
Small: 5-7%
Medium: 8-10%
Large: 6-8%
Target: Cost Overrun
≤ 2%
Formal Change-Order Process
Written change requests
Priced change orders
Client sign-off required
15% premium after week 2
Target: Change Orders
≤ 30% of projects
Supplier Management
Negotiate SLAs for lead times
Maintain safety stock
Build backup vendor list
2% penalty for delays
Target: On-Time Delivery
≥ 90%
Flexible Labor Planning
Trusted subcontractor roster
Pre-book for festival seasons
Cross-train staff
Peak season surcharge
Target: Average Delay
≤ 2 days
Proportional Timeline Buffers
Replace fixed 2-day buffers
Add 5-10% of duration
Higher for medium projects
Monitor daelays weekly
Target: Buffer Coverage
≥ 85%
Treat Time as Cost
Track delay costs in real-time
0.13% cost per delay day
Early warning system
Delay as cost overrun indicator
Target: Profit Margin
+4-5% improvement

## Slide 10
Slide 10: Expected Outcomes
Improved Profitability
4-5%
Immediate Profit Improvement
40-68%
Reduction in Profit Erosion
Data-driven buffers for accurate cost estimation
Cost overruns reduced from 6.76% to ≤2%
Recovery of ₹539,184 from top 3 issues
Better Customer Satisfaction
50%
Reduction in Delays
85%
On-Time Delivery Rate
Realistic timelines with proportional buffers
Clear change-order process with client approval
Transparent pricing reduces surprises
Competitive Advantage
15%
Market Share Growth
30%
Referral Business Increase
Reputation for reliable delivery in Pune market
Confidence to handle larger projects
Stronger supplier relationships
Business Growth
25%
Annual Revenue Growth
2x
Project Capacity
Scalable operational processes
Improved resource allocation
Foundation for sustainable expansion